UBC Utilities Service Standard for Campus Development

| UBC Board of Governors Approval Status | Development Information Provided to UBC Utilities | UBC Utilities Support Services | Response Time (Maximum) | UBC Utilities Fee |
| --- | --- | --- | --- | --- |
| Pre-Board Preparations | Type of development sought (e.g. housing, research, industrial); Number of buildings and units; define short list of proposed locations. | General advice on development process, where to obtain records, services available. Consultation on site services available; identify critical utility servicing issues. | 3 weeks | None |
| Board 1 Approval: Project in principle, location, donor agreement | Confirm number of buildings, number of units, identify utility services needed. Provide a preliminary site plan drawings. | Range of expected cost of servicing; consultation on site services available; viability to relocate services if needed. | 3 weeks | None |
| Board 2 Approval: Preliminary capital & operating budgets, schedule, select consultant, proceed with schematic design. | Provide a site plan drawing based on field survey. Final list of services desired, including energy source for heat. Re-confirm number of buildings, units, and usage. Provide building and unit occupancy estimates. | Revised cost estimate for servicing. | 3 weeks | None |
|  |  | Conduct field inspections to locate underground services, verify records. | 3 weeks | $300 fixed fee per utility service per site. |
| Board 3 Approval: Schematic design, proceed with drawings & tender. | Provide pre-tender site plan. Provide estimated average and peak loads, and service connection sizes (e.g. pipe and cable sizes) for all desired utility services. | Run system engineering models to assess impact on existing infrastructure. Re-evaluate water fire flow requirements if significant re-development of fire flow zone. | 4 weeks | None |
| Board 4 Approval: Final capital & operating budgets, award construction contract. | Provide construction tender documents and addendums. | Specify and procure meters. | Size and order within 2 weeks. Delivery lead time by supplier. | At cost. |
|  |  | Service shutdowns (Application Required) | 2 weeks | $200 fixed fee per shutdown if M-F 7:30-3:30; or $350 after hours or weekends. |
| Board 5: Project completion report. | Provide copies as-built service drawings (originals to CP&D). Provide actual construction costs. | Review development process, costs, actual energy consumption, etc. as agreed. | 4 weeks | None |